## Simple Safety Risk Register (hidden)
SIMPLE SAFETY RISK REGISTER TEMPLATE
RISK ID | RISK DESCRIPTION | IMPACT DESCRIPTION | IMPACT LEVEL | PROBABILITY LEVEL | PRIORITY LEVEL | MITIGATION NOTES | OWNER | KEY
1 | Difficulty in creating an intuitive user interface and experience | Bad UI of application and ultimately users will avoid using our application, resulting in potential loss | 4 | 4 | 16 | Conduct user testing at various stages, involve stakeholders in design reviews, and employ experienced UX/UI designers | UI Lead, Mr. Farhan | 1
2 | Insufficient integration with agricultural data sources leading to inaccurate recommendations. | Irrelevant recommendations to users resulting in bad harvest and imporper agricultural practices of users. | 4 | 2 | 8 | Regularly update data sources, conduct thorough testing of crop management algorithms, and collaborate with agriculture experts for validation | Dev lead, Mr. Ahmed Usman | 2
3 | Lack of user engagement and participation in community features | interest-less application might result in significant decrease of user adoption. | 3 | 3 | 9 | Implement gamification elements, incentivize participation, and have a community manager actively facilitate discussions | Marketing and CP lead, Hira Rehman & Aisha Memon | 3
4 | Compatibility issues with external APIs or data source changes | this might result in incorrect information to users eventually decreasing usability. | 5 | 3 | 15 | Regularly check for API updates, implement version control, and establish backup mechanisms for critical data | Dev lead, Mr. Ahmed Usman | 4
5 | Failure to comply with data protection regulations leading to legal issues | restrictions will be imposed which might lead to banned application in regions. | 4 | 1 | 4 | Regularly update privacy policies, implement robust encryption measures, and stay informed about relevant data protection laws | Compliance and SOP sector-head, Mr. Hamza Ahmed | 5
6 | Lack of user interest and low adoption rates. | this might result in decreased revenues and ultimately vanishing out of the market | 5 | 1 | 5 | Conduct marketing campaigns, offer incentives for early adopters, and continuously gather user feedback for improvements | UI Lead, Mr. Farhan
7 | Inability to adapt to changing technological trends and user preferences. | chances are high to get eliminated from the market and users may abondon using this app. | 3 | 3 | 9 | Keep the development process agile, conduct regular technology assessments, and have a feedback loop for continuous improvement | Technical Lead, Mr. Kashif bhai
CLICK HERE TO CREATE IN SMARTSHEET

## FSPM-RISK-REGISTER
RISK ID | RISK DESCRIPTION | IMPACT DESCRIPTION | IMPACT LEVEL | PROBABILITY LEVEL | PRIORITY LEVEL | MITIGATION NOTES | OWNER | KEY
1 | Difficulty in creating an intuitive user interface and experience | Bad UI of application and ultimately users will avoid using our application, resulting in potential loss | 4 | 4 | 16 | Conduct user testing at various stages, involve stakeholders in design reviews, and employ experienced UX/UI designers | UI Lead, Mr. Farhan | 1
2 | Insufficient integration with agricultural data sources leading to inaccurate recommendations. | Irrelevant recommendations to users resulting in bad harvest and imporper agricultural practices of users. | 4 | 2 | 8 | Regularly update data sources, conduct thorough testing of crop management algorithms, and collaborate with agriculture experts for validation | Dev lead, Mr. Ahmed Usman | 2
3 | Lack of user engagement and participation in community features | interest-less application might result in significant decrease of user adoption. | 3 | 3 | 9 | Implement gamification elements, incentivize participation, and have a community manager actively facilitate discussions | Marketing and CP lead, Hira Rehman & Aisha Memon | 3
4 | Compatibility issues with external APIs or data source changes | this might result in incorrect information to users eventually decreasing usability. | 5 | 3 | 15 | Regularly check for API updates, implement version control, and establish backup mechanisms for critical data | Dev lead, Mr. Ahmed Usman | 4
5 | Failure to comply with data protection regulations leading to legal issues | restrictions will be imposed which might lead to banned application in regions. | 4 | 1 | 4 | Regularly update privacy policies, implement robust encryption measures, and stay informed about relevant data protection laws | Compliance and SOP sector-head, Mr. Hamza Ahmed | 5
6 | Lack of user interest and low adoption rates. | this might result in decreased revenues and ultimately vanishing out of the market | 5 | 1 | 5 | Conduct marketing campaigns, offer incentives for early adopters, and continuously gather user feedback for improvements | UI Lead, Mr. Farhan
7 | Inability to adapt to changing technological trends and user preferences. | chances are high to get eliminated from the market and users may abondon using this app. | 3 | 3 | 9 | Keep the development process agile, conduct regular technology assessments, and have a feedback loop for continuous improvement | Technical Lead, Mr. Kashif bhai

## Scale
RISK REGISTER SCALE
P R O B A B I L I T Y | 5 | 5 | 10 | 15 | 20 | 25
| 4 | 4 | 8 | 12 | 16 | 20
| 3 | 3 | 6 | 9 | 12 | 15
| 2 | 2 | 4 | 6 | 8 | 10
| 1 | 1 | 2 | 3 | 4 | 5
|  | 1 | 2 | 3 | 4 | 5
I M P A C T

## - Disclaimer - (hidden)
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.
Risk Id